PART 1 – GENERAL

1.1	RELATED DOCUMENTS

- Applicable portions of the Project Manual including but not limited to the Drawings and Specifications.

1.2	SUMMARY

- This Section includes administrative and procedural requirements governing allowances.

- Definition:

Allowances. “’Allowance’ is an amount which is established between the Owner and the CONTRACTOR as part of the bid documents when the precise scope of a particular line item(s) has not been defined to a level which is adequate for the CONTRACTOR to provide a definitive line item pricing for that particular scope of Work.

1.3	COORDINATION

- At the earliest practical date after award of the Contract, the Contractor shall advise Owner of the date when final selection and purchase of each product or Work described by an Allowance must be completed to avoid delaying the Work.

- Coordinate Allowance items with other portions of the Work. Furnish templates as required to coordinate installation.

1.4	PROCEDURES

- .1	Non-Mobilization Allowances

- Submit cost proposals for purchase of products or work included in Allowances in the form specified for Change Orders.

- Coordinate and process submittals for Allowance items in accordance with Section 01300 as for other portions of the Work.

- The use of any Allowances by the CONTRACTOR will be subject to the Owner’s sole approval and it is the Owner’s intent to minimize the use of Allowances to the fullest extent possible.

- For any Allowances which the Owner allows the CONTRACTOR to use, the following rules shall apply: (i) the Allowance shall cover the cost to the CONTRACTOR of the cost of Work, as defined in the Agreement and the CONTRACTOR’s portion of overhead and profit associated with the stated Allowance; and (iii) upon completion of the portion of the Work subject to an Allowance, the Contract Amount for that portion of the Work will be adjusted based upon the approved actual Cost of the Work, including the proportionate overhead and profit.

- .2	Mobilization Allowance

- An Allowance is provided with this Contract for the mobilization of personnel, equipment and materials at the Work site for other contract items that will be performed by the CONTRACTOR.  Mobilization shall include, but not be limited to the movement of equipment, personnel, material, supplies, etc. to and from the Work site; and the installation of necessary facilities (when not paid for separately) prior to the initiation of the Work and their removal at the completion of the Work.

PART 2 – PRODUCTS

- NOT USED

PART 3 – EXECUTION

3.1	SCHEDULE OF ALLOWANCES

Project Managers need to define the scope of work for the Allowances. [See examples below. Note: The examples below are provided to indicate the type of information that should be included in the scope of work for the Allowance.]

Delete this instruction box prior to printing.

EXAMPLES:

Allowance No. 1 – Furniture Allowance			$50,000

This is for the purchase and installation of Office Furniture for the Administration Building.

Allowance No. 2 – Mobilization Allowance	$10,000.00, generally include 8% of the total contract authorization as the mobilization allowance.

3.2		MEASUREMENT AND PAYMENT

.1	Non-Mobilization Allowance

Once the cost proposal for the Allowance has been incorporated into the Contract by Change Order, Payment for the Allowance will be based upon either the unit prices or a schedule of values provided with the proposal and incorporated in the Change Order.

.2	Mobilization Allowance

If an Allowance for Mobilization is included in the 00300 Unit Price Bid  Form the Contractor shall be entitled to a lump sum payment for Bonding, Insurance, and Mobilization for each assignment issued by the Owner as follows:

.1  Bond and Insurance: 2% of the value of the assignment

.2  Mobilization

.1  $1,500 for assignment value less than or equal to $25,000

.2  6% of the assignment value for assignments greater than $25,000 and less than or equal to $500,000

.3  2% of the assignment value for assignments greater than $500,000.

.4 If the Contractor is currently working at a facility on other Work not associated with this Work, the Contractor shall submit the actual cost of mobilization for new equipment to be brought on-site that are solely attributable to this Work.

The sum of Bond, Insurance, and Mobilization shall be paid under one Mobilization pay item added by change order and credited against the Allowance for Mobilization.

When 1% of the Work Assignment is earned 50% of the Mobilization will be paid.

When 5% of the Work Assignment is earned the balance of the Mobilization will be paid.”

END