## Class Selection
ESTIMATE CLASSIFICATION
| CLASS 5 | CLASS 4 | CLASS 3 | CLASS 2 | CLASS 1
DESIGN PHASE | Concept Screening | Feasibility Report | Schematic Design | Design Development | Construction Documents
MATURITY LEVEL OF PROJECT DEFINITION DELIVARABLES | 0% to 2% | 1% to 15% | 10% to 40% | 30% to 75% | 65% to 100%
ESTIMATE GOAL | Long Range Planning | Bond Proposal or Dept. Facility Master Plan | Bond Proposal or Design Budget Authorization | Project Budget Monitoring | Project Budget Monitoring
Deliverables
Scope | Scope is articulated at basic general level. Function of building, major program elements, rough estimate of square foot area | Scope is articulated at further refined conceptual level. Function of building is defined beyond general use to more specific description of functions and need. Major program elements are further refined and given conceptual areas. Design Criteria Manual articulating Owner’s Project Requirements (OPR) provided | Scope is articulated at Schematic Design level with formal Basis of Design (BOD) document. All program elements are defined and given net usable areas. | Refined as per Design Development documents | N/A
Schedule | Desired occupancy date based on department’s facility master plan | Update desired occupancy date and set target dates for Design, Construction Start, and Substantial Completion | Update desired occupancy date and set target dates for Design, Construction Start, and Substantial Completion | Updated Occupancy Date, Design Document Submissions, Permitting, Bidding, Construction Start, and Substantial Completion | Updated Permitting, Bidding, Construction Start, and Substantial Completion
Team | Sponsor SPOC and Project Manager | Sponsor SPOC, Project Manager, and in-house or rotation list design professionals | Sponsor SPOC, Project Manager, and in-house or rotation list design professionals | Sponsor SPOC, Project Manager, and rotation list design professionals | Sponsor SPOC, Project Manager, rotation list design professionals and sub-consultants
Comparisons | Provide at least 4 comparable projects from City of Austin or similar cities with total project cost. Also provide photos and basic floorplans | Provide/update at least 4 comparable projects from City of Austin or similar cities with total project cost broken down in COA Project Budget Form format. Also provide photos and basic floorplans | Provide/update at least 4 comparable projects from City of Austin or similar cities with total project cost broken down in COA Project Budget Form format. Also provide photos and basic floorplans | N/A | N/A
Site Information - Not Selected | estimate a site improvement cost based on desired location (i.e. downtown (high), suburban (med), or rural (low)). If a specific site has not been selected then cost of land purchase should be included in budget form | Net site area required for building footprint and parking; Zoning required for proposed use; Comprehensive Plan alignment goals; Utility requirements | N/A | N/A | N/A
Site Information - Selected | provide location of site with aerial photograph and description of current condition of site. Cost of site improvements should be calculated into the construction cost estimate | Surveys on record; Soil information from historical data; Slope information noting non-buildable areas and areas that required significant earthwork; Hydrology: Flood plain impact if any; Hydrology: Water quality infrastructure requirements noted but not estimated; Existing trees particular heritage trees; Property’s current zoning, adjacent zoning and assessment of ap propriateness; Property’s buildable area and envelope: Setbacks, building height, allowable impervious coverage; Comprehensive Plan alignment; Demolition, HazMat, and other potential mitigation factors noted but not fully estimated; Utility connection requirements noted but not estimated | Site Information based on site owned by COA or under contract - Survey of property with boundary, easements, setbacks, utilities, topography, structures, pavement and trees located; Geotech report based on proposed building location; Site work: Conceptual grading plan with cut-fill calculations and utility location requirements; Hydrology: Site drainage and water quality infrastructure facilities developed to conceptual level; Property’s current zoning, adjacent zoning and assessment of appropriateness; Property’s allowable vs. proposed buildable area and envelope; Comprehensive Plan alignment updated; Demolition, HazMat, and other mitigation factors researched and estimated; Utility connection requirements estimated | Site Design Development Documents | Site Design Permit Documents
Estimating Tools | D4Cost, RS Means Square Foot Cost, ENR Quarterly Cost Roundup | D4Cost, RS Means Square Foot Cost, RS Means Building Construction Cost Data, Consultant Cost Estimator | RS Means Building Construction Cost Data, Consultant Cost Estimator | Consultant Cost Estimator | Consultant Cost Estimator
Floor Plans | N/A | Floor plans provided at “bubble diagram” level illustrating size & relationship of major program elements relative to each other | Provided at Schematic Design level of quality | Provided at Design Development level of quality | Provide at Building Permit level of quality
Elevations & Building Sections | N/A | N/A | Provided at Schematic Design level of quality | Provided at Design Development level of quality | Provide at Building Permit level of quality
Structural Engineering | N/A | N/A | Conceptual plan and narrative provided | Provided at Design Development level of quality | Provide at Building Permit level of quality
MEP Engineering | N/A | N/A | narrative provided | Provided at Design Development level of quality | Provide at Building Permit level of quality
Site Design Permit | N/A | N/A | N/A | N/A | Provide Site Plan Development Permit
Building Permit | N/A | N/A | N/A | N/A | Provide Building Permit